## Proposal (25-26)
S.No | Domain | Different Avenues of the testing scope | Overview of the methodology | Key Dilevirables | Key Dependencies | Est.testdate | Est.startdate | Timeline of testing | Timeline of remediation | Stake holder | Last tested year | Requirement statements
1 | Web Application | Authentication, Authorization, Input Validation | OWASP Top 10 based testing | Vulnerability Report, Remediation Guide | Test Environment Access | 2024-03-15 | 2024-03-01 | 2 weeks | 1 week | IT Team | 2024-25 | Comprehensive web app security testing
2 | Network Infrastructure | Firewall, IDS/IPS, Network Segmentation | NIST Cybersecurity Framework | Network Security Assessment | Network Documentation | 2024-04-20 | 2024-04-01 | 3 weeks | 2 weeks | Network Team | 2024-25 | Network infrastructure assessment
3 | Mobile Application | API Security, Data Storage, Communication | OWASP Mobile Top 10 | Mobile Security Report | Source Code Access | 2024-05-10 | 2024-05-01 | 2 weeks | 1 week | Development Team | 2024-25 | Mobile application security review

## Scope (24-25)
S.No | Penetration testing | Description | Key Dilevirables | Key Dependencies | Est.testdate | Est.startdate | Timeline of testing | Timeline of remediation | Stake holder | Last tested year | Requirement statements | Impact of these tests
1 | Web App Penetration Testing | Testing web application for security vulnerabilities | Detailed vulnerability report | Application access and credentials | 2024-03-15 | 2024-03-01 | 2 weeks | 1 week | IT Team | 2024-25 | OWASP Top 10 compliance testing | HIGH
2 | Network Penetration Testing | Testing network infrastructure for security gaps | Network security assessment report | Network topology and access | 2024-04-20 | 2024-04-01 | 3 weeks | 2 weeks | Network Team | 2024-25 | PCI DSS network compliance | CRITICAL
3 | Mobile App Testing | Testing mobile application for security issues | Mobile security test report | Mobile app binary and source code | 2024-05-10 | 2024-05-01 | 2 weeks | 1 week | Development Team | 2024-25 | OWASP Mobile Top 10 testing | MEDIUM

## VAPT Results
Vulnerabilities ID | Name of vulnerability | Description | Tested environment | Result | Reporting evidence | Source of identifcation | Criticiality based on CVSS score | Criticiality based on business context | Stake holders | Remarks from stakeholders
VAPT-2024-001 | SQL Injection in Login Form | SQL injection vulnerability found in user login form allowing data extraction | PRODUCTION | FAIL | Screenshot showing successful SQL injection | Manual Testing | HIGH | CRITICAL | IT Team, Security Team | Critical fix required immediately
VAPT-2024-002 | Unencrypted Network Traffic | Network traffic between client and server is not encrypted | STAGING | FAIL | Network capture showing unencrypted traffic | Network Analysis | MEDIUM | HIGH | Network Team | Implement SSL/TLS encryption
VAPT-2024-003 | Insecure Data Storage | Sensitive data stored in plain text on mobile device | DEVELOPMENT | FAIL | File system analysis showing plain text data | Code Review | HIGH | MEDIUM | Development Team | Update data encryption methods